## Sheet1
Source | Data connectivity | ETL | Location standardization | Crop standardization | Season standardization | UOM standardization | Staging layer | Reporting layer | Location granularity | Metrics from the source | Final status | Comments
DES State level | Done | Done | Done | Done | Done | Done | Done | Done | State | APY | Done
DES District level | Done | Done | Done | Partially Done | Partially Done | Done | Done | Done | District | APY | Partially Done | 1. Estimate Type not mentioned so we have considered the data to be for Final Estimate. 2. Clarification pending on Whole Year in Season column. Ignored entries for Whole Year for now and processed data.
MNCFC/Remote Sensing | Done | Done | Done | Done | Done | Done | Done | Done | District | APY | Done
IEG/Econometric modelling | Done | Done | Done | Done | Done | Done | Done | Done | State | APY | Done
CWWG | Done | Done | Done | Done | Done | Done | Done | Done | State | Area | Done
State published | Done | Done | Done | Done | Done | Done | Done | Done | State | APY | Done
NSSO | Done | In-Progress | Pending | Pending | Pending | Pending | Pending | Pending | State | Yield | Pending
Farmer's survey | In-Progress | In-Progress | Pending | Pending | Pending | Pending | Pending | Pending | State | Yield | Pending
Sammunati | Done | Done | Done | Done | Done | Done | Done | Done | State | APY | Done
PMFBY | In-Progress | Hold | Hold | Hold | Hold | Hold | Hold | Hold | Village | Yield | Hold | The API accepts district codes as inputs. The district codes are not the LGD codes as per PMFBY. Waiting for PMFBY to share their district master.
GCES | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Village | Yield | Pending | No discussion for this source.
DCS | In-Progress | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Village | Area | Pending | API development in progress. Waiting for DCS API.
NDVI | In-Progress | Done | In-Progress | - | - | - | Done | In-Progress | District, Tehsil | NDVI | In-Progress | API yet to be shared. Current ETL pipeline is based on website scraping.
Rainfall data | In-Progress | In-Progress | In-Progress | - | - | - | Pending | Pending | District, Tehsil | Rainfall | Pending | API yet to be shared. Current ETL pipeline is based on website scraping.
LUS | Pending | Done | Done | Partially Done | Partially Done | Done | Done | Done | State | Area | In-Progress | File shared with historical data.No mechanism yet to share upcoming data.